## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP
0 | 9/11-9/24 | Finished SPPP Created first draft of app Decided on app Analyzed potential risks | 1. Put GitHub repo in the wrong location 2. Took too much time debugging 3. Jira was not visible to all members | 4. Not using Jira 5. Leaving work to last minute when others are reliant on said work 6. Member missed meeting | 1. Resolved 2. Use AI to help with debugging 3. Resolved 4. Create standards and present at meeting 5. Set deadlines for individual pieces that other work relys on 6. All members will be present in-person for meetings | 0 | 0 | 6 | 3 | 3 | 98 | 82 | 16 | 12.5 | 22.5 | 10 | 14.5 | 3 | 15 | 6 | 2
1 | 9/25-10/15 | Created Database and APIs Created backbone for frontend | 1. Tests were not working on all computers 2. Difficulties setting up Docker | 2. Lack of communication - leading to duplicate work | 1. Work as a team to debug problem 2. Resolved 3. Everyone create and use Jira, everyone push to GitHub more frequently, make smaller pull requests | 5 | 13 | 17 | 12 | 7 | 321 | 301 | 20 | 32.5 | 23.5 | 42 | 70.5 | 37.5 | 16.5 | 65.5 | 13
2 | 10/16-11/5 | Added 3 games Study sessions, goals, buddy exp, and buddy status are all scored Buddy picture exists User progress can be seen UI improvement for timer Unit and integration tests added -------- Work that got done but didn't end up in release version: Calendar to view study sessions UI improvement for game menu Acceptance tests | 1. Expo mobile is not working 2. Difficulties with linting 3. Enviroments didn't match - sometime having old versions of node modules 4. IPs didn't match across devices | 5. Pull requests not being reviewed 6. Deadlines not followed or changed | 1. This was fixed with deleting the entire repo and doing a clean clone 2. Members that got linting working will aid members that are having difficulties 3. Delete node modules folder and do a clean install 4. Create a .env files where members can put individual IP addresses into 5. Reduce the needed reviews down to 1 6. Have more reminders, assign critical work to members that consistantly make deadlines, and make members create their own deadlines | 34 | 53 | 19 | 9 | 17 | 235 | 212 | 23 | 27.5 | 23 | 28 | 66 | 20 | 17.5 | 17.5 | 12.5 | Test coverage: 32.21% Test Case Execution Rate: 100% Pass Percentage: 100% Automation Rate: 90% Review Coverage: 100%
3 | 11/6-12/3 | Finalised study buddy pet system (naming, death/reset logic, state updates) Study timer counts down instead of up. Completed UI polishing for the app Performed extensive manual testing + coverage Improved CI/CD with added security checks and docker builds (for prod and dev) Deployed app on render | 1. Merge conflicts caused by late PRs and outdated branches | 1. Pull requests not being reviewed 2. Members not adhering to code freeze deadlines | - | 63 | 0 | 11 | 30 | 0 | 216.5 | 195.5 | 22 | 29 | 26 | 24.5 | 61 | 14.5 | 11 | 16.5 | 13 | Frontend test coverage: Statements: 68% Branches: 33% Functions: 43% Backend test coverage: Statements: 82% Functions: 81% Lines: 88% Pass Percentage: 100% Automation Rate: 90% Review Coverage: 98%

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Ittoop Shinu Shibu | I contributed to the SPPP by authoring and maintaining the Configuration Management Plan, the Tools section, and the Branching Strategy. This included defining the entire CI/CD workflow, specifying GitHub Actions pipelines, describing version control policies, documenting security scanning tools (CodeQL, TruffleHog, OSV Scanner), and detailing how Docker, GitHub, and automation tools integrate throughout the project lifecycle. | As the Requirements Leader, I was responsible for converting discussion points into well-structured Jira tickets, refining user stories, adding acceptance criteria, and breaking down large requirements into actionable subtasks. I reorganized unclear or vague stories, discussed proper prioritization for each iteration with the team lead and members of the team. I also collaborated with team members weekly to adjust scope, remove infeasible features, and ensure that requirements aligned with project deadlines and professor/TA feedback. | I authored the initial Class Diagram section, including system-level class relationships, frontend component diagrams, and descriptions of all major screens, components, and state-management structures. Team members made edits on top of the class diagram I created. | I did not contribute to the STD beyond checking if everything was updated accurately. This is because updating the STD was assigned to other teammates. | I contributed to the preparation of the final presentation by detailing the projects configuration management and requirement management details.I also contributed to the first presentation. | My implementation work primarily focused on implementation of features, CI/CD setup and fixes, and Docker environment configuration. I maintained the backend/frontend Docker compatibility, resolved environment variable conflicts, supported new feature developments (such as the study timer that was entirely written by me as well as the tests), and helped address failing pull requests caused by testing or bugs, Docker, or pipeline issues. I also assisted with debugging merges, reviewing code, branch conflicts, and integration problems between frontend and backend code. | I contributed manual testing throughout all iterations, focusing on workflow validation across all features. I also developed tests for new features such as the study timer feature. | As the Configuration Management Leader, I was responsible for the design, setup, and maintenance of the entire CI/CD pipeline, Docker infrastructure, and deployment configurations. I implemented multi-stage Dockerfiles for frontend (dev and prod) and backend, configured docker-compose for local development, integrated automated testing into GitHub Actions, and ensured all images built successfully before merging. I also managed Render deployment settings, resolved container compatibility issues, enforced PR testing standards, and ensured that every build passed security scans and dependency checks. | I played a large role in sprint planning, Jira refinement, and team coordination from the second iteration onwards (which is when I took over the requirements leader role). I actively participated in every meeting, tried to provide clarity on expectations, assisted members facing technical blockers (Docker, Git, CI/CD errors), and reviewed pull requests to maintain project quality. I also helped ensure documents were correctly updated before iteration deadlines. I also tried to actively communicate with team members. Even though I missed 2 meetings, I still checked with the team to ensure I was caught up on what I missed so that I could continue actively participating with the team.
Melissa Cron | Wrote and updated Management plan through semester | During the first half of the semester as requirements manager, wrote all tickets on Jira. During the second half of the semester, wrote bug tickets and updated my tickets as well as other tickets that were not updated. | Wrote the introductions and the API logs | Wrote and updated Manual testing reports | Wrote and presented iteration 0 and 3. Consulted for iteration 1 and 2 presentations. | Contributed to the following pages on the frontend: settings and home. Contributed to the following routes and models for the backend: buddy. Designed and implimented most components including: Buddy, Navigation Button, Form Submit Button, and more. | Created and executed several manual tests as described in the STD. With the help of Cursor, wrote many automatted tests for both the frontend and backend. When other students had difficulties passing the automatted tests, often helped them troubleshoot or even rewrote their code/tests to fix broken tests. Designed buttons that change status to help with testing. | Helped troubleshoot when other members could not run the docker or deployment | Planned and ran all meetings. Consistantly reminded members of deadlines through discord. Set deadlines. Assigned priorities to tasks.
Junzhe Chen | Worte and updated Quality Assurance Plan through semester | In Jira, I wrote user stories that I felt were necessary. | Wrote a part of Unit Test | Wrote and updated UI design, security design | Wrote and presented iteration 2 and 3. | I primarily participated in front-end development. I also assisted with connecting to the front-end and writing the front-end code. I also tried writing some test cases. My main focus was front-end development, including page design, button design, and contributing AI-generated images of friends. | Several manual tests were created and executed. Chatgpt was primarily used to create many tests based on input requirements. Additionally, changes were made to the test code after modifications were made to the front-end code. | The main deployments come from the use of EXPO GO, as well as the use of DOCKER. | I participated in all Discord meetings, both online and offline, in a timely manner. I also took some meeting minutes.
Bohan Lin | Wrote overview and related work. | Wrote Jira tickets and update tickes taht are assgined to me. | Update class diagram and wrote design pattern and software architecture. | Wrote manual testing and automated testing. | In charge of iteration 1 presentation. In final presentation, in charge of backend design and security part. | Wrote backend structure, including routes, models, and database. Wrote frontend login, calendar screen. Wrote frontend auth state. | Wrote backend unit testing and integration testing. | Cloud deployed backend server on render. | Took three meeting minutes and took part in three
Dexiao Zhang | QA-related activities, clarified testing scope, and helped define risks, metrics | Add and refined user stories related to authentication ,buddy system,event cpapcity rules,and query prevention, | helped document the backend architecture, clarified the MVC structure, and contributed to the REST API documentation by specifying request/response formats, status codes, and workflow details. | Wrote and updated backend and frontend testing documentation, including manual test reports, automated test summaries, and testing metrics. | Presented iteration 1 and final presentation; delivered Study Buddy overview and testing sections. | Implemented backend features (registration init, buddy setup, attendee/capacity validation), built extensive unit and integration tests with full CI support, improved backend coverage, fixed major bugs, updated DB schema/config, and assisted with debugging and refactoring across multiple backend modules. | Wrote and maintained backend unit/integration tests, improved test coverage, configured CI test environment, and performed extensive manual and regression testing; also helped teammates debug failing tests. | Configured backend test environment (SQLite for CI), helped troubleshoot deployment/testing issues, and assisted teammates with backend setup and CI failures. | Actively coordinated QA tasks, communicated testing needs and deadlines, supported teammates with debugging, and contributed to overall project communication.
Qiuting Zhao | Wrote and u[detaed Proposed High level Requirements through semester | Wrote Jira tickets for user stories that are essential for the game part, and updated the tickets that are assigned to me | Wrote and updated Business Logic and/or Key Algorithms, including the pseudocode, flow chart, and sequence diagrams. | Wrote manual testing for game timer restrictions. | Presented iteration 2 and in charge of the entire game section of the final presentation. | I designed and implemented the gameplay logic for all three mini-games: Game1: gravity, jump physics, platform generation, collision detection, scrolling world. Game2: obstacle spawning, difficulty scaling, collision behavior, survival scoring. Game3: shooting angle calculation, projectile movement, enemy spawning, hit detection. I also implemented shared game timer hook (useGameTimer), full score system frontend, including fetching high scores and updating new scores, navigation flow improvements for Game Menu & Game Screens, and multiple bug fixes (timer not stopping, game loop running after exit, navigation crashes) | Created automated frontend tests for Game1, Game2, Game3, and GameMenu using Jest + React Native Testing Library. Performed extensive manual testing on gameplay behavior, including physics tuning, collision edge cases, performance issues, and timer bugs. Verified score storage and frontend–backend integration. | Helped other members troubleshoot Expo GO issues when games had rendering or performance problems. Worked through conflicts in feature branches and fixed local environment errors related to running the frontend. | Discussed with team members the necessary features we need, both functional and non functional.

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Melissa Cron
Your Lead Roles: Project Leader, Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 6 | 4 | 2 | 0 - learning 1 - Created 1st draft of Requirement Document 2 - design 3 - implementation 4 - test 5 - Scheduled meeting, used meeting to determine project choice, answered questions about GitHub 6 - setting up GitHub 7 - unclassified |  | 2 |  |  |  | 1 | 1 |  |  | 1. Write first draft requirements document 2. Finished lab 1 | 1. Project subject was changed multiple times 2. Meeting ran long | 1. During our second meeting, the entire group decided on a project subject and it will not be changed now 2. Team leader (me) will create better plan before meetings and try to stick to it | 0 - learn how react interacts with mobile devices 1 - change requirements document to fit ideas from group 2 - design 3 - implementation 4 - test 5 - communication/management 6 - set up personal coding enviroment and jira 7 - unclassified | 5
2 | 9/18 - 9/24 | 4.5 | 4 | 0.5 | 0 - learning 1 - requirement analysis 2 - design 3 - created README.md and formatted team.md 4 - test 5 - meeting notes, helped people join Jira, added to risk management document, did Management Plan in SPPP document 6 - moved github repo to correct location 7 - worked on iteration 0 presentation |  |  |  | 0.5 |  | 2 | 0.5 | 1 |  | 1. wrote meeting notes 2. added to risk management document 3. did management plan in SPPP document 4. worked on iteration 0 presentation | 1. People are not creating nor tracking Jira tickets 2. Individual pieces are not finished soon enough to do the work that requires them | 1. Create standards and present at meeting 2. Set better deadlines | 0 - learning 1 - requirement analysis 2 - design 3 - create first interface 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | 5
3 | 9/25 - 10/1 | 12.5 | 11.5 | 1 | 0 - how to use Jira 1 - turned requirements document into Jira Epics 2 - design 3 - Moved pages from html to React, moved the css, and created the timer for the studying page 4 - test 5 - reviewed other members commits 6 - set up Expo Go 7 - unclassified | 1 | 0.5 |  | 8.5 |  | 0.5 | 1 |  | Consulted ChatGPT about how to use specific React Native functions. |  | 1. code for webpages written in HTML instead of React Native | 1. I rewrote them in React Native | 0 - learning 1 - requirement analysis 2 - design 3 - create interface for goals 4 - review other people's code 5 - communication/management 6 - help member set up GitHub 7 - unclassified | 8
4 | 10/2-10/8 | 6.5 | 5 | 1.5 | 0 - learning 1 - create 2 stories 2 - created 1st draft for Buddies 3 - reviewed pull requests 4 - test 5 - communication/management 6 - failed to get Docker to work 7 - unclassified |  | 1 | 1 | 0.5 |  |  | 2.5 |  |  | 1. Worked on lab 2 | 1. Could not get Docker working 2. Kimi wrote code for a section of the project I already finished the code for | 1. Ask for help from Shinu our Configuration leader 2. He will pull from GitHub and copy over only the code that is not already existing | 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - get docker working 7 - unclassified | 8
5 | 10/9-10/15 | 8.5 | 7.5 | 1 | 0 - consulting software professionals about how to be a better project leader 1 - requirement analysis 2 - design 3 - prepared my branch for pushing by adding comments, fixed accessbility roles 4 - fixed broken API tests 5 - messaging people to make sure the documents get done on time 6 - finally got Docker working 7 - updated SDD, summary for progress report | 2 |  |  | 1.5 | 1 | 0.5 | 0.5 | 2 | I used AI to figure out how to fix a broken test and a broken expo command. It gave me a few different possible solutions, one of which was correct. | 1. updated SPP 2. worked on SDD 3. did summary for progress report | 1. A new page was created without first pulling the existing pages - thus not following the formatting standards 2. A significant amount of work is being done but not ending up on GitHub. I do not know where the code is | 1. The person who did this will pull the existing work and update to match that work 2. Talk to the members involved and impress on them that any work needs to be communicated and updated. Also, encourage smaller pull requests | 0 - learn more project management strategies 1 - requirement analysis 2 - design 3 - do implimentation task 4 - test 5 - make sure people are communicating and documenting their progress 6 - configuration/environment 7 - unclassified | 8
6 | 10/16-10/22 | 10 | 9 | 1 | 0 - consulted teacher about project management strategies 1 - requirement analysis 2 - design 3 - fixed bug for npm package.json, added input and display for custom goal, created modular Cat svg, added Buddy to the front page that changes based on data 4 - test 5 - talked to team about Jira management, reviewed pull requests 6 - configuration/environment 7 - unclassified | 1 |  |  | 7 |  | 1 |  |  | Consulted when code didn't work. It was much less effective today, needing several prompts to give a useful answer. I basically used it as a rubber duck | N/A | 1. frontend and backend integration required to finish ticket | 1. resolved | 0 - learning 1 - requirement analysis 2 - design 3 - finish the tickets I picked up this week 4 - create unit tests for frontend, do lab 3 5 - ask people for updates halfway through the week 6 - configuration/environment 7 - unclassified | 8
7 | 10/23-10/29 | 10 | 7.5 | 2.5 | 0 - consulted busness manager about meeting efficiency 1 - requirement analysis 2 - design 3 - prepared buddy branch for pull review 4 - used Cursor to develop unit tests 5 - meeting minutes, reminding people to do their work, planning for next meeting, updating Jira to prioritize tasks to finish by the end of iteration 2 6 - configuration/environment 7 - unclassified | 0.5 |  | 2 | 2.5 | 0.5 | 2 |  |  | Used Cursor to generate specific functions. The specifics had to be modified, but the outline was well written. | 1. meeting minutes | 1. Tasks are assigned and members accept the task - but then they don't finish within the assigned time 2. Work is being done without starting a pull request - thus it is not ending up in the project | 1. Ask for better estimates 2. Require finishing work before starting new work | 0 - learning 1 - create plan for iteration 3 2 - design 3 - finish buddy database update ticket started last week 4 - test 5 - prepare for meeting 6 - configuration/environment 7 - unclassified | 8
8 | 10/30-11/5 | 14 | 13 | 1 | 0 - learning 1 - requirement analysis 2 - design 3 - fixed PR requests to match develop, created system to update exp and status of buddy 4 - fix game1 to work with linting, create acceptance tests using AI 5 - reminding people about pull requests and deadlines, plan meeting 6 - configuration/environment 7 - write summary for progress report |  |  |  | 8 | 2.5 | 2 |  | 0.5 | Inputted bug and a little code and ChatGPT gave the one line fix |  | 1. Many team members are not reviewing pull requests 2. Coders are making the files too big instead of splitting them into separate files | 1. Come up with a plan during the next meeting to fix this 2. Create tasks to refactor the code when nessisary - making this technical debt | 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - design meeting, assign jobs 6 - configuration/environment 7 - refactor code to split big files | 8
9 | 11/6-11/12 | 8.5 | 7.5 | 1 | 0 - trying to figure out if Oauth is possible 1 - requirement analysis 2 - design 3 - username and password validation, reset buddy on death, tried to fix buddy values not bringing up right numbers 4 - test 5 - updating Jira based on group meeting, planning next meeting 6 - configuration/environment 7 - unclassified | 1.5 |  |  | 5 |  | 1 |  |  |  |  | Previous pull request isn't working |  | 0 - learning 1 - requirement analysis 2 - finish elements needed for app to be finished 3 - implementation 4 - create more integration and unit tests 5 - plan next meeting 6 - configuration/environment 7 - unclassified | 8
10 | 11/13-11/19 | 13 | 12 | 1 | 0 - learning 1 - requirement analysis 2 - design 3 - change buddy model to prevent status from going out of bounds; manage, review, and pull pull requests 4 - fixing tests that fail for pull requests, create test for buddy model 5 - reviewing pull requests, planning for the next meeting 6 - configuration/environment 7 - unclassified |  |  |  | 5 | 4 | 3 |  |  | Created tests for a function including boundry constraints and edge cases. cursor_create_tests_for_buddymodel_upda.md | Meeting minutes | 1. Team member assigned to write meeting minutes did not do so | 1. I will do it for them | 0 - learning 1 - requirement analysis 2 - design 3 - finish jira tasks 4 - test 5 - remind people about Code Freeze 6 - configuration/environment 7 - update REAMME | 12
11 | 11/20-11/26 | 8.5 | 7.5 | 1 | 0 - learning 1 - requirement analysis 2 - design 3 - change the colors on two screens, did a lot of UI work, fixed a pull request, added Buddy's name to the home screen 4 - fixed some tests that broke when features were added 5 - communication/management 6 - configuration/environment 7 - unclassified |  |  |  | 7 | 0.5 | [7 empty] | 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | 8
12 | 11/27-12/3 | 6 | 4.5 | 1.5 | 0 - learning 1 - requirement analysis 2 - design 3 - added rate limiting 4 - test 5 - enforced Code Freeze 6 - configuration/environment 7 - presentation, create demo video, prepared code for merging |  |  |  | 1 |  | 0.5 |  | 3 | https://drive.google.com/file/d/1RVNQvQGA2ahBp4ctK8-M147rhV_Fuj7D/view?usp=sharing Created rate-limiting with AI | Presentation Demo video | 1. Develop won't merge into main | 1. Temporarily override develop protections to allow pushing a merge-conflict-fix | 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - create presentation | 5

## Dexiao Zhang
Your Lead Roles: Design & Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 11 | 9 | 2 | 0 - Discussed project requirements 1 - studied git ，GitHub ，I/O，HTTP 2 - work on sppp6 | 1 | 7 | 1 | [5 empty] | chatgpt for learning git and so on | set the enviorment about git,write sppp6 |  |  |  | 9 | backend develop
2 | 9/18 - 9/24 | 9 | 8 | 1 | 0 - work on lab1 and write the report 1 - learn how to use stocker and jira 2 - write the lab2 3 - learn the framework we use in project | 1 | 1 | 2 | 4 |  |  |  |  | chatgpt for learning jira and how to set the enviorment about stocker | search the framework,commit profile to github |  |  |  | 9
3 | 9/25-10/1 | 22 | 21 | 1 | 0 - Researched Docker, Express, JWT, and SQLite integration for backend authentication. 1 - Set up backend project structure (server.js, db.js, routes/, models/) and environment configuration using .env and dotenv. 2 - Implemented user registration and login APIs using bcrypt + JWT for secure authentication. 3 - Debugged token verification middleware (auth.js) and ensured protected routes work correctly with JWT. 4 - Collaborated with teammate Bohan on user endpoints and database initialization. 5 - Configured Swagger documentation for backend API endpoints. 6 - Created early unit tests for /api/users/register and /api/users/login routes using Jest and Supertest, verifying 200/400/401 responses. | 4 | 3 | 4 | 3 | 2 | 2 | 3 |  | Used ChatGPT occasionally for syntax debugging and Jest error explanations. Also used it for writing sample curl requests and test setup examples. | Built and tested backend authentication module (JWT). Added working API documentation through Swagger. Contributed to early unit test coverage for /api/users. | JWT token not recognized across requests SQLite path errors in Windows environment Swagger not rendering new endpoints | Fixed by adding consistent Authorization header in middleware Fixed by using path.resolve(process.cwd(), DB_PATH) Fixed by refreshing swaggerSpec registration in server.js | 1.Implemented SQLite models for each module and linked them via foreign keys 2.Added energy decay logic to Buddy model to simulate health/energy drop over time. | 20
4 | 10/2-10/8 | 26 | 25 | 1 | 0 - Extended backend APIs to include Buddy, Profile, Settings, and Study routes. 1 - Implemented SQLite models for each module and linked them via foreign keys. 2 - Wrote and debugged integration and system tests (system.test.js, buddyAPI.test.js, etc.) using Jest and Supertest. 3 - Set up .env.test and __tests__/setupEnv.js to run isolated test databases automatically. 4 - Fixed test-related database issues (foreign key constraint, missing table) and improved test coverage. 5 - Added energy decay logic to Buddy model to simulate health/energy drop over time. 6 - Worked closely with Bohan to merge backend CI branch and ensure all endpoints pass authentication + test validations. 7 - Assisted frontend team with API integration for login and buddy features. | 4 | 2 | 5 | 3 | 2 | 3 | 4 | 2 | Used ChatGPT for explaining SQLite ON CONFLICT behavior and schema design tips. Verified all AI suggestions manually before committing to the repository. | Completed backend models and routes for all core features. Established and debugged automated testing pipeline. Validated energy decay logic and database schema consistency. Contributed to CI readiness for backend testing environment. | Jest tests timing out due to foreign key constraints Test database using incorrect path 500 errors during CI runs Some endpoints returning 401 in tests | Resolved by reordering table deletion and enabling PRAGMA foreign_keys = OFF during cleanup Fixed by resetting DB_PATH to ./db/test.sqlite under test mode Traced to missing start_time/end_time columns; fixed in schema Added consistent token validation middleware |  | 15
5 | 10/9-10/15 | 9 | 8 | 1 | 0 - Prepare the presentation for Iteration 1 1 - Achieved decay value 2 - SDD file design and software architecture section. | 2 | 4 | 2 | [5 empty] | Used ChatGPT selectively for test script review | improve energy decay logic to Buddy model which all pass the test |  |  | achieve personalized study rewards | 15
6 | 10/16-10/22 | 15.5 | 14 | 1.5 | 0 - Implemented attendee and user routes integration 1 - Updated Dockerfile and docker-compose for backend 2 - Refactored database schema and model validations 3 -Testing & QA | 3 | 2 | 4 | 5 |  |  |  |  | Used to debug Docker build errors and Jest test failures. | I contributed to the backend deliverables of the StudyBuddy project. I implemented and tested backend routes for users and attendees, updated the database schema validations, and fixed environment variable issues in the Docker setup. | Encountered Docker connection errors when running backend tests inside containers. Fixed by adjusting docker-compose service names and environment variables. | Continue improving backend test coverage and add error-handling cases for invalid requests. |  | 15
7 | 10/23 - 10/29 | 20.5 | 18 | 2.5 | 0 - Integrated frontend testing infrastructure into project repository. 1 - Implemented unit tests for LoginForm, NavigationButton, Home, and AuthContext components. 2 - Refactored test files and added mock providers for React Navigation and AsyncStorage.Coordinated test structure under __tests__/ and aligned with project CI flow. | 7 | 8 | 3 | [5 empty] | Used ChatGPT extensively to debug Jest mock issues | Finalized complete frontend unit testing setup (Jest + React Native Testing Library). Created and validated unit tests for all major components (LoginForm, AuthContext, NavigationButton, Home). Achieved stable 100% pass rate and ~80% coverage. | Encountered repeated missing module errors (NativeAnimatedHelper), afterEach undefined bug, and context provider failures. | All issues resolved after environment refactor and Jest setup fixes; frontend test suite now stable and CI-ready. | Extend tests to utility and statistics modules; assist teammates in merging PRs and preparing iteration demo. | 15
8 | 10/30 - 11/5 | 16 | 15 | 1 | 0 – Reviewed CI pipeline and debugged frontend test execution in containerized environment. 1 – Analyzed dependency issues and module resolution failures (react-native-calendars, mock providers). 2 – Refactored Jest config and package.json scripts (test:ci) to enable CI testing. 3 – Executed tests using Docker command docker run --rm -w /app studybuddy-frontend:ci npm run test:ci, validated environment setup. | 5 | 3 | 4 | 3 |  |  |  |  | Used ChatGPT to diagnose test failures and mock environment issues, get guidance on Jest CI configuration and Docker workflow adjustments. Helpful for quickly identifying missing dependencies and path fixes. | Stabilized CI test pipeline for frontend; | Encountered module not found error |  | Extend CI coverage to include frontend utility and API tests. | 15
9 | 11/6 -11/12 | 15 | 14 | 1 | 0 –mock calendar, redesign test config 1 – fixing Jest config, refactor imports 2 – Jest failures, docker test runs 3 – CI container tests, mock provider fixes | 3 | 4 | 4 | 3 |  |  |  |  | Used ChatGPT to diagnose Jest test failures, mock provider issues, and module resolution errors. Received guidance on fixing react-native-calendars import failures, adjusting Jest configuration, and running tests inside Docker CI. AI assistance was helpful for identifying missing dependencies and resolving environment inconsistencies quickly. | Fixed broken frontend test suite, restored Jest execution, and stabilized CI test pipeline for the frontend. Improved test configuration and dependency resolution for the team. |  | Resolved most issues; remaining environment inconsistencies will be addressed by updating mocks and aligning package versions in the next iteration. |  | 15
10 | 11/13-11/19 | 13 | 12 | 1 | 0 –Implementation migration rebuil DB 1 – Test 2 – Configuration/Environment check docker sql | 5 | 3 | 4 | [5 empty] | Used ChatGPT to diagnose issues with the initial backend database setup, including missing SQLite files, failed migrations, and incorrect environment configuration. The AI tool guided me through rebuilding the database, rerunning migrations, and verifying that tables and records were properly created. This assistance helped identify the root cause of missing data and ensured the initialization process worked correctly. | Set up, validated, and repaired the backend’s initial database. Rebuilt the SQLite database, fixed migration issues, and ensured all initial tables were generated correctly. Verified data loading and confirmed that the backend can properly connect and read the rebuilt database. | Initial database file was missing or not fully created, causing empty tables and backend read failures. | Resolved by recreating the database and rerunning migrations. Next step is to verify seed data loading in the upcoming iteration. |  | 15
11 | 11/20-11/26 | 16 | 15 | 1 | 0 – Writing new tests 1 – Running tests, fixing failing tests, verifying coverage 2 – Configuring coverage tools, CI integration, adjusting jest / backend test setup 3 – Designing additional test cases | 3 | 3 | 4 | 5 |  |  |  |  | Used ChatGPT to generate and refine new frontend and backend test cases, troubleshoot failing tests, and resolve issues with coverage configuration. AI assistance also provided guidance on integrating coverage into the CI pipeline and improving mock setups for stable test execution. | Implemented additional frontend and backend test cases and significantly improved overall code coverage. Configured and stabilized coverage reporting for both services and ensured the CI pipeline correctly displays updated metrics. Enhanced test reliability by refining mocks, utilities, and failing test logic. | Coverage reports were not generated correctly due to misconfigured test environments and missing mocks. Several initial tests failed after adding new cases. | Resolved by adjusting the test configuration, rewriting unstable tests, and correcting coverage settings. Plan to continue increasing backend coverage in the next iteration. |  | 15
12 | 11/27-12/3 | 10 | 10 | 1 | 0 – Reviewing and refining design sections for the final SDD submission. 1 – Reviewing final test results, verifying coverage numbers, and updating testing sections in the STD. 2 – Coordinating with teammates for final deliverables, confirming test completeness and documentation deadlines. 3 – Preparing and polishing the final presentation (Study Buddy overview + testing), completing contribution tables, and finalizing course deliverables. | 2 | 4 | 2 | 2 |  |  |  |  | Used AI tools to refine final presentation scripts, summarize testing documentation, and polish SDD/STD sections. AI assistance also helped generate concise contribution statements and improve clarity in final deliverables. | Prepared final presentation slides and script (Study Buddy overview + testing). Finalized testing documentation, updated SDD/STD sections, and completed individual contribution reporting. | No major technical issues; work focused on documentation and final presentation preparation. | Deliverables completed; ready for final submission.

## Junzhe Chen
Your Lead Roles: Security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 8 | 6 | 2 | 0 - learning 1 - Study Git 2 - design the basic UI 3 - implementation 4 - test 5 - meeting 6 - setting up GitHub | 2 | 2 | 1 | 1 | 1 | 1.5 | 1 | 0 | Chatgpt, Midjourney | Write first draft document Finished lab 1 | project subject change many times | in the second meeting, we decide the subject | do the demo of our project. work on pres | 5
2 | 9/18 - 9/24 | 11.5 | 11 | 0.5 | 0 - learning use AI graph 1 - write on lab 1 2 - SPPP update 3 - project 4 - test | 1 | 1 | 1 | 6 | 2 | 0 | 0 | 0 | chatgpt, gemini | wrote meeting notes added to risk management document did management plan in SPPP document write a demo of our project | use many time to debug | used Ai | do the more detail | 10
3 | 9/25 - 10/1 | 21 | 20 | 1 | 0 - learning Expo Go, Native 1 - Use ant-icon to beautify the UI 2 - Add setting, and study time display 3 - test 5 - find click sound and buddy picture | 4 | 3 | 10 | 2 | 0 | 1 | 0 | 0 | Chatgpt, Midjourney, gemini, nano banana | Frontend study timer page Connect all page in the frontend | need more resourse to build UI | Try to use more professionalism tools | Make the program run | 10
4 | 10/2 - 10/8 | 31.5 | 30 | 1.5 | 0 - learning Pixso, Figma, Flutter 1 - Use Figma to create a demo of home page 2 - Use Pixso to build a calender page 3 - Test two pages | 5 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | Chatgpt, Midjourney, gemini, nano banana, Figma, Pixso | Calender page Home page Buddy information page | Build a beautiful page is too difficult for me | Learned Figma and use Figma to build my page | Try to beautify other pages. | 10
5 | 10/9 - 10/15 | 8 | 7 | 1 | 0 - learning React native, Expo go 1 - connect html.file to React native | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Chatgpt, deepseek | Personal information page. | Many files can run normally individually, but the buttons inside cannot be used to switch pages. | Solve the issue in the next week. | Try writing all the files in html | 10
6 | 10/16 - 10/22 | 22 | 21 | 1 | 0 - Try to let tsx file change to js file 1 - Implemented frontend login screen to connect to backend API. And use my Login page UI. 2 - Make a demo of timer 3 - Try to draw a ERD digram of our SQL | 10 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | Figma, Chatgpt | Login page, timer | When connecting to endpoint APIs, localhost can not be used. | I investigated the issue step by step. First, I set up an output for the database contents. I checked whether the database could read the data. Next, I set up an interface in the homepage interface to see if it could read the data correctly. Finally, I found the problem. That is by changing localhost to IPv4 address, the endpoint API is successfully connected in frontend. | Still change the html file that I have to js file. | 10
7 | 10/23 - 10/29 | 5.5 | 3 | 2.5 | 0- Understand the functionality of the game page 1- Try communicating with the game page's creator 2- Try using figma to change the appearance. | 1 | 1 | 1 | [5 empty] | chatgpt, nanobanana, gemini, figma, github copilot | Figma's demo on the game page | It's unclear what kind of background is needed. | Group meeting discussion | Group presentation PPT | 10
8 | 10/30 - 11/ 5 | 17 | 16 | 1 | 0 - Do the game menu 1 - write test file 2 - do presetation slide | 7 | 3 | 6 | [5 empty] | chatgpt, nanobanana, gemini, figma, github copilot | Game menu page, change the background about home, game menu, home page | Many components are incompatible. | Try using alternatives that do not require additional installation. | Style, css, button change | 10
9 | 11/6 - 11/12 | 7.5 | 6.5 | 1 | 0 - check and update button/style 1 - review pull and requires | 5.5 | 1 | [6 empty] | chatgpt, github copilot | The main issue addressed was the inconsistency in the components used in the user interface. | There's an interface I won't change. | We have already communicated with the production team. | Create a home page | 10
10 | 11/13 - 11/19 | 7 | 6 | 1 | 0 - Update style 1 - review pull and requires 2 - gen AI buddy | 3 | 1 | 2 | [5 empty] | nanobanana, chatgpt, sora, google ai studio | picture of buddy, style and button | buddy not looks cute | Try to use more professionalism tools | make more emotion picture about buddy | 10
11 | 11/ 20 - 11/ 26 | 4 | 3 | 1 | 0 - unclassified | 3 | [7 empty] | None | None | Need to prepare the final speech | Next week meeting | Prepare Presentation | 10
12 | 11 / 27 - 12 / 3 | 8.5 | 7 | 1.5 | 0 - Find bugs 1 - finish final presentaion slide 2 - Finish SDD | 2 | 4 | 1 | [5 empty] | Chatgpt， Kimi | Final presentation slide， SDD | Present not well | Group meeting to discuss | Rewiew | 5

## Ittoop Shinu Shibu
Your Lead Roles: Configurations Leader/Requirements Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/11-09/17 | 9 | 6 | 3 | 6 - Set up Jira and configure github 1 - worked on SPPP 1 - Researched on CI/CD, branching and code review strategies 1 - Researched on frameworks 5 - Discussed what our project is going to be about |  | 2 |  |  |  | 3 | 1 |  | ChatGPT - for research into the configuration management portion of the SPPP | 1. Worked on the configuration management portion of the SPPP 2. Conducted research into how to implement CI/CD 3. Set up github repo 4. Set up jira board for the team 5. Looked into the different frameworks we could potentially use for our application 6. Researched branching strategies 7. Researched code review strategies to implement for the team | 1. We were unsure of what application we were going to build for our project 2. The Jira board was not visible to everyone | 1. Resolved, we went through a couple rounds of discussions and decided on what we are building 2. Resolved, made the jira board visible to everyone | 1 - continue to work on SPPP 1 - continue research for the SPPP configuration management portion of the document | 2
2 | 9/18-9/24 | 5.5 | 4 | 1.5 | 6 - Commited changes to new github repo and reviewed PR as the old one was incorrect 1 - Continued to work on SPPP 1 - Continued to research for SPPP on configuration management 1 - Added risks of configuration management into risk document 5 - Went through deliverables and blockers in group meeting in stand up style 7 - worked on powerpoint presentation on group project |  | 2 |  |  |  | 0.5 | 0.5 | 1 | ChatGPT - for research into the configuration management portion of the SPPP | 1. Completed the configuration management portion of the SPPP 2. Conducted research into configuration management 3. Committed any missing changes from old github repo to the new repo 4. Worked on powerpoint presentation on group project 5. Added in configuration management risks into risk document | 1. We realised that the previous repo we created was incorrect and our commits needed to be shifted | 1. Resolved, the old repos contents were shifted to the new repo | 1 - Begin working on iteration 1 2 - set up rulesets on github for branching and clean up branches 3 - begin setting up CI/CD | 6
3 | 9/25-10/1 | 11 | 10 | 1 | 6 - Started to set up CI/CD 6 - Set up git to autodelete branches 6 - Added in code scanning for security 5 - Discussed and agreed on CI/CD approach. Linting and testing to be managed by CI/CD. No pull requests to be merged without the passing of the tests once CI/CD has been setup. Also discussed others progress on their items. 0 - Read up on setting up jest and testing for react native applications 0 - Read up on linting packages using for react native applications | 2 |  |  |  |  | 1 | 7 |  | ChatGPT - for research into CI/CD setup, bug fixing issues with CI/CD setup Github Copilot - for creation of files for CI/CD, bug fixing issues with CI/CD setup | 1. Researched what a CI/CD setup should look like by looking at old repos submitted for this class and researching via ChatGPT. 2. Set up CI/CD for frontend with linting functionality for the time being, as the test setup still had a lot of issues that needed to be fixed. Backend code was not in the branch I was referring to yet so I could only create code for the frontend 3. Set up git to autodelete branches | 1. Faced a lot of issues with setting up CI/CD on the frontend code. We encountered numerous parse issues with Babel, TypeScript, and Flow in the test setup, which took us hours to debug. Most of the time was spent debugging the code to fix this issue. | 1. Not resolved, this will be pushed to next week. | 1. Continue working on getting CI/CD set up | 10
4 | 10/2-10/8 | 16 | 15 | 1 | 6 - Continue setting up CI/CD 6 - Set up docker for our project 0 - read up on how docker works 5 - Discussed issues that I am facing on the CI/CD and what I should provide for docker to the team for lab 2 during team meeting. Also discussed others progress on their items. | 1 |  |  |  |  | 1 | 13 |  | ChatGPT - bug fixing issues with CI/CD setup Gordon (Docker's Agent) - Quick start guide on docker, creation of docker files and bug fixing | 1. Continued trying to get CI/CD set up. I tried to create mocks to circumvent the type script + flow parse errors jest was throwing 2. Set up docker for the project, divided into backend and frontend. provided the docker files to the team and asked the team to review the code | 1. Continued to face issues with this even with creating mocks this week. Most of my time was spent on debugging this issue. Also tried to look at other teams code but no one seems to have used react native. | 1. Not resolved, this will be pushed to next week. | 1. Continue working on getting CI/CD set up | 10
5 | 10/9-10/15 | 19 | 18 | 1 | 6 - Finish setting up CI/CD 7 - Code review 4 - Bug found in develop branch due to docker 5 - Discussed what we need to finish up for the upcoming iteration of the project. 7 - Work on class diagrams for SDD |  |  |  |  | 3 | 1 | 12 | 2 | ChatGPT - bug fixing issues with CI/CD setup Github Copilot - Help to create an initial class diagrams based on our code. | 1. Managed to get the CI/CD setup for both backend (after backend code was pulled into my branch this week) and frontend. Managed to fix the issue of setting up jest switching to jsdom instead of using jest-expo. It was quite hard to fix this, a large amount of time was spent debugging this issue. 2. Completed code review on the completeWebsiteLayout branch. This branch contained all the frontend code for iteration 1. 3. Worked on class diagram for SDD 4. Checked everyone else's additions to the project before we submit 5. Fixed bug where there was a package missing in package.json in the develop branch |  |  | 1. To pick up tickets from the icebox story items on "Recommend study goals based on history and research" and "Global and friends leaderboard for study progress" | 10
6 | 10/16-10/22 | 9 | 8 | 1 | 5 – Reviewed PR #18 (simple login frontend code using backend API) 6 – Drafted Docker + Expo runbook and environment setup notes 6 – Investigated .local .env configuration issues and documented fixes 5 – Planned next steps for compose cleanup and frontend auth feedback 1 – Created user stories and tickets for Iteration 2 in project board | 0 | 2 | 0 | 0 | 0 | 3 | 3 | 0 | Used OpenAI Codex to draft Docker/Expo runbook steps and refine login UX copy; verified suggestions locally. | Code review for PR #18 (simple login frontend); prepped Docker+Expo runbook and docker-compose cleanup; outlined auth feedback items. | Login endpoint env configuration varied by teammate machines. | Documented .env usage and IP config; proposed default dev profile in compose. | Finalize hotfix PR for Docker/Expo runbook and compose cleanup; Start working on timer UI improvements and frontend + backend implementation | 20
7 | 10/23-10/29 | 20 | 19 | 1 | 6 – Wrote and submitted hotfix PR #26 (Docker + Expo runbook, compose cleanup, auth feedback) 5 – Reviewed PR #23 (buddy pictures) 2 and 3 - reworked PR #25 (timer feature) by implementing backend and frontend integration + UI improvements 6 – Standardized compose network naming and added Expo cache-clear instructions 3 – Tested and verified Docker/Expo integration after hotfix changes 4 - Added test cases for timer UI frontend and backend + frontend implementation | 0 | 0 | 2 | 8 | 2 | 1 | 6 | 0 | Used Codex for docker-compose service definitions, README snippets and developing timer UI and integration; spot-checked output. | Opened PR #26: Docker+Expo runbook, compose cleanup, and frontend auth feedback; iterated on comments; reviewed PR #23 (buddy pictures) and PR #25 (timer). | Expo iOS build caching led to stale bundle; compose network naming conflicts. | Added clear cache steps to runbook; standardized compose service names. | Review PR's and wait for comments on my PR's | 10
8 | 10/30-11/05 | 5 | 4 | 1 | 6 – Merged hotfix PR #26 and implemented SVG conversion in PR #32 (for React Native) 6 – Merged Dependabot PR #33 (security update for tar) 3 – Debugged and verified React Native SVG rendering across platforms 5 – Reviewed and approved PR #23 final merge (buddy pictures) | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | Used Codex to generate SVG component scaffolds and small refactors; manual testing of RN rendering. | Merged PR #26 on 11/01; opened & merged PR #32: convert SVGs for React Native; merged Dependabot PR #33 (tar security bump) after checks; reviewed PR #23 final changes. | Some custom SVGs failed to render in RN WebView/native. | Added react-native-svg, converted assets, and hardened fallback logic for buddy data. | Integration testing across iOS/Android; small UI polish; Add new features | 8
9 | 11/6-11/12 | 8 | 8 | 0 | 1 - Created tickets for iteration 3 3 - Worked on refactoring study timer code 1 - Researched how to implement security into CI/CD 1 - Researched deployment |  | 3 |  | 5 |  |  |  |  | Used codex to refactor study timer code Used ChatGPT to help generate tickets | Created tickets for the team; Worked on refactoring study timer to fit project template; Implementing security into CI | Not really familiar with security so i had to do a lot of research | Planning to implement security next week into CI | Implement security into CI | 8
10 | 11/13-11/19 | 13 | 12 | 1 | 6 - Worked on implementing Security Into CI 5 - Reviewed validate/sanitize login (#46) and Feature/reset buddy on death (#47) 1 - Continued to look at how to deploy app via docker 3 - Worked on implementing count down logic for timer and fixing UI issues |  | 2 |  | 2 |  | 1 | 7 |  | Used codex to help with implementing security into CI | Reworked study timer, one of the main features for our app; Worked on implementing security into CI and deployment; | - | - | Finish deployment, security into CI and review PRs | 12
11 | 11/20-11/27 | 17 | 16 | 1 | 6 - Added security CI workflow (CodeQL, TruffleHog, OSV) and dependency bumps (#68) 6 - Added dev/prod Docker split for frontend and compose tweaks (#69) 3 - Completed and pushed Refactored study timer logic/UI and styles (#67) 3 - Implemented count down logic for timer 3 - Made slight changes for Fixed navigation flow and updated login/home tests(#70) by adding safe areas into page 6 - Deployed frontend to render 5 - Reviewed PRs #74, #73, #66, #64, #59, #54, #53 |  |  |  | 4 |  | 4 | 8 |  | Used codex for implementation of code | Implemented security into CI; Implemented deployment for frontend; Implemented Study timer (one of the main features for the app); Reviewed PRs for other features; | - | - | Work on presentation and SPPP; | 2
12 | 11/27-12/3 | 5 | 5 | 0 | 7 - Worked on presentation slides for configuration management and requirement analysis 7 - Worked on SPPP 5 - Reviewed and approved PR #83 | [5 empty] | 0.5 |  | 4.5 | - | Worked on presentation slides for configuration management and requirement analysis; Worked on SPPP | - | - | - | -

## Qiuting Zhao
Your Lead Roles: Design & Implementation Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 7.5 | 6.5 | 1 | 0 - research different stack, install development tools and learn 1 - analyzed target users, confirmed app’s overall style and aesthetic direction 5 - attended project meeting and documented meeting notes. 6 - set up coding environment | 3 | 1.5 |  |  |  | 1 | 1 |  | Use chatgpt to research and compare different stacks | 1. Write meeting notes 2. Set up git 3. Finished Lab1 | The type of project was hesitant for a long time | Solved, made final decision during 2nd meeting | 0 - Learn how React works 2 - Design some mini game prototypes 7 - Finished iteration0 documents | 10
2 | 9/18 - 9/24 | 7 | 7 | 0 | 0 - learn React and Jira, find a lot of mini game prototype online 3 - implement some mini game to try and test 5 - work on Proposed High level Requirements in SPPP file, add to RiskManagement file 6 - join the github repo | 2.5 |  |  | 3 |  | 1 | 0.5 |  |  | 1. Write one section of SPPP 2. Add to RiskManagement file | Missed group meeting | Will go in-person in the future | 5 - Discuss soft friction alternative for iOS device restrictions | 10
3 | 9/25 - 10/1 | 17.5 | 16.5 | 1 | 0 - learn expo, RN, RN web 2 - design Game1 structure and constants 3 - import outer libraries to help render 5 - discuss the AI usage possibilities for UI 6 - configure build environment and fix import / module errors when running outside libraries | 1 | 0 | 2.5 | 4 |  | 1 | 8 |  | Used ChatGPT to understand how to call outside libraries that help render game from React Native, including import path setup and module export adjustment. Helpful for resolving bundler and rendering issues. | 1. Setup Game1 branch 2. Completed GameMenu basic layout and navigation structure. 3. Verified screen transition logic between Home and GameMenu. 4. Configured and tested Expo development environment for React Native and web platforms. | 1. Laptop Broken :( 2. Expo startup failure and persistent blank screen on both simulator and web preview. 3. Environment mismatch between React version and installed dependencies. | Solved 1. Buy a new one 2. Reinstalled and reconfigured Expo CLI and React 19 environment 3. Cleared cache, rebuilt node_modules, and verified compatibility 4. Confirmed GameMenu running successfully on simulator and web after fix. | 0 - Learn how to implement and render inside React directly 2 - Design more games 3 - Finish the implementation of Game1 7 - Finished Lab2 documents | 20
4 | 10/2 - 10/8 | 19 | 17.5 | 1.5 | 0 - research how to integrate helper libraries into React Native environment 3 - implement player movement, gravity, and jump mechanics, implement collision detection, player controls, and scoring system 4 - manual test Game1 gameplay, including win and lose conditions, test rendering across devices 5 - discuss UI consistency, discuss platform and environment usage 6 - debug import and module errors | 3.5 |  |  | 7 | 2 | 1 | 4 |  | Used ChatGPT to help understand and render the game and animation inside React Native. Helpful since import outside helper libraries is nearly impossible, solve the render problem. | 1. Designed Game1 (GolfMe) structure and gameplay constants (gravity, jump, scroll). 2. Tested performance on web and Android. 3. Maintained visual consistency with layout. | 1. Import failure due to ESM module path issue. 2. The game ratio is strange and screen is black 3. Gameplay speed inconsistency across devices. 4. Expo hot reload crash during game script execution. | Solved 1. Used AI to instead the import methods 2. Adjusted gravity and frame update rate. | 2 - Design game 2 gameplay 3 - Integrate reusable components and scoring 4 - Automatic test and Unit test for games, also the CI/CD 7 - Finish iteration 1 | 25
5 | 10/9 - 10/15 | 31.5 | 30.5 | 1 | 2 - refine UI design for Game1, design Game2 structure and constants 3 - complete Game2 implementation with core logic and gameplay loop 4 - conduct detailed multi-device testing (Game1 & Game2) focusing on performance and rendering 5 - discuss further functionalities, and some restrictions for game part to make it suitable for our app 6 - fix React Native runtime warnings and optimize code structure |  |  | 4.5 | 10 | 12 | 1.5 | 2.5 |  | Used ChatGPT to investigate why several test cases always failed, including version mismatch between React Native and Expo SDK. Also used it to check dependency compatibility, rebuild environment, and analyze logs from failed runs. Very helpful for environment diagnosis and test debugging. | 1. Completed Game2 gameplay logic using React Native physics and event system. 2. Improved scoring accuracy and collision stability. 3. Conducted detailed manual cross-platform testing on web, iOS, and Android. 4. Identified and documented unsolved test failures and runtime inconsistencies. 5. Key algorithms part in SDD file | 1. Environment conflict: mismatch between React 19, Expo SDK 52, and React Navigation version. 2. Testing configuration issue: serious incompatibility between Babel, Vitest, and Jest in handling React 19 JSX transforms. 3. The transpilation flow cannot be properly transferred — Babel compiles JSX for Metro bundler, while Vitest reprocesses the same files with different ESM rules, and Jest expects CommonJS modules. As a result, test runs failed to import components correctly, producing “Unexpected token import/export” and “Cannot use import statement outside a module” errors. | Unsolved 1. Shinu said this may be fixed since there was a recent hotfix for this, try next week | 2 - design another 3 games 3 - time restrictions for users who enter the game menu, and rewards for high scores | 30
6 | 10/16 - 10/22 | 24 | 23 | 1 | 2 - designed Game3 and Game4 logic 3 - implemented foundational gameplay functions for Game3 and Game 4, adjusted shared constants and rendering parameters, modify the game values for Game1-4 to be more reasonable 4 - finished unit test for Game1 and Game2 5 - discussed with teammates how they can help with the game manual test 6 - completed the game part testing setup after shinu's hotfix |  |  | 4 | 11 | 5.5 | 0.5 | 2 |  | Used ChatGPT to assist with balancing game parameters and to generate unit-test stubs for React Native modules; helpful for identifying test scope and checking syntax issues after hotfix integration. | 1. Game3 and Game4 logic designed and partially implemented. 2. Unit tests for Game1 and Game2 completed. | 1. Gameplay speed varies significantly between portrait modes on mobile and landscape modes on computer, likely due to aspect ratio causing balance issues. 2. Occasional unit-test failures due to Expo SDK caching. | Solved 1. The issue of unplayable speed on mobile portrait mode has been fixed by adjusting movement and timing to be ratio-based rather than absolute values. But I still wang to explore switching the mobile version to landscape mode for a more comfortable and engaging gameplay experience 2. Continuous test whether the failures will occur again | 3 – implement study-time-based gameplay limitation (countdown timer and unlock mechanism) 4 – write test cases for the timing logic | 10
7 | 10/23 - 10/29 | 13.5 | 12.5 | 1 | 2 - designed Game5 3 - optimized games rendering ratios for different devices, confirmed responsive design works properly 4 - fixed compatibility issues in testing configuration after hotfix 5 - discussed about the UI design for game 5 - finish Jira board |  |  | 2 | 6 | 3.5 | 1 |  |  | No AI Usage this week | 1. Whole game page (gameMenu, games) | 1. Merging conflicts 2. Unit test mock problem | Solved | 2 - Refine the game settings and parameters to make it more balanced 3 - Time restrictions for game time 5 - Let team members help manual test the game too see if it's reasonable across devices | 15
8 | 10/30 - 11/5 | 10 | 10 | 0 | 2 - re-design all scoring system and parameters to make the game more resonable 3 - implemented study-time-based gameplay limitation (timer & unlock logic) 4 - manual test the time restriction function 5 - presentation 6 - build(fix) the environment for login page on mobile devices |  |  | 3 | 1.5 | 1 | 2 | 2.5 |  | Used ChatGPT to identify and resolve React 19 + Vitest + Babel compatibility errors, and to adjust Jest configuration for Metro bundler. | 1. All responsible doc files 2. Iteration 2 slides | 1. API_BASE_URL: undefined Auth endpoint: undefined/users/login Login page does not work on expo 2. Merge and push to wrong branches | Unsolved 1. Suspect wifi problem, try later Solved 1. Revert wrong PR | 3 - Design and implement the reward system for game, link the score record to users' databases | 20
9 | 11/6 - 11/12 | 10.5 | 9.5 | 1 | 2 – Refine the core mechanics and parameter tuning of the mini-games module to improve consistency 3 – Enhance movement, timing, and object-generation logic across the mini-games 4 – Build initial Jest smoke tests to ensure stable rendering and basic interaction reliability 6 – Manage local branches, use stash to isolate partial work, and sync with develop for team integration |  |  | 2 | 4 | 2 |  | 1.5 |  | Used ChatGPT to compare different RN test strategies and navigation mocking patterns. Helpful for identifying minimal wrappers required for Jest. Applied the suggestions manually after validating compatibility. | 1. Refined mini-game logic 2. Created initial Jest tests 3. Prepared test environment. | Difficulty stabilizing navigation context inside Jest. | Partially resolved by adding wrapper components; further adjustment planned next week. | 4 - Deepen test coverage | 10
10 | 11/13 - 11/19 | 8 | 8 | 0 | 0 – Investigate mocking strategies for animation and navigation components 2 – Restructure mini-games internal logic for improved maintainability 3 – Refactor loops and object-interaction sections for stability 4 – Expand unit tests and resolve failures triggered by navigation behavior | 1 |  | 2 | 2 | 3 |  |  |  | Used ChatGPT to analyze why some tests fail with RN animations | none | Snapshot tests remained unstable due to animations. | Will avoid snapshot testing for animated components and focus on behavior-based tests. | 3 - Implement play-study time restrictions and link game score to user | 12
11 | 11/20 - 11/26 | 9.5 | 9.5 | 0 | 1 – Analyze requirements for integrating the “study-time unlock” mechanism into the mini-games module 2 – Design the logic flow for unlocking games based on accumulated study minutes and define threshold rules 3 – Implement the unlock-check mechanism and integrate it with the existing user session data 3 – Develop the structure for recording and updating the user’s highest scores across all mini-games 4 – Test unlock triggers, verify score persistence, and debug discrepancies in stored values |  | 1 | 0.5 | 6 | 2 |  |  |  | none | 1. Implemented the core framework for the learning-time-based unlock system and added persistent high-score tracking to the mini-games module. | The forced locking of the game interface did not work. | Unsolved | 4 - Test more about the new adding components | 5
12 | 11/27 - 12/3 | 8 | 6.5 | 1.5 | 2 – Refine the study-time unlock mechanism by improving threshold checks and ensuring consistent behavior across different session lengths 4 – Conduct multi-session testing to validate persistence of unlock states and high scores across app restarts 7 - Prepare the presentation slide |  |  | 3 |  | 2 |  |  | 1.5 | none | 1. All responsible doc files 2. Final presentation slide(my part) | Some desired features have not yet been implemented. | May continue implementing in the future

## Bohan Lin
Your Lead Roles: Design & Implementation Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 11 | 9 | 2 | 0 - Studied Agile, scrum, and Jira 1 - Discussed project requirements 2 - Designing the technology stack for the project | 1 | 3 | 5 | [5 empty] | Use ChatGPT for research technology stack that will be used in the project | 1. Research possible stack that will be used |  |  | finish iteration 0 with required documents filled | 10
2 | 9/18 - 9/24 | 8 | 7.5 | 0.5 | 0 - Review course material and documents 1 - Work on lab1 and lab1 report 5 - Work on SPPP files and SPPP_RiskManagement 6 - Set up Github and Jira | 1 | 1 |  |  |  | 5 | 0.5 |  | Use ChatGPT for research related work of our project | 1. Set up git, push team.md to lab1 branch 2. Write 2 sections of SPPP |  |  | start iteration 1 with demo code | 10
3 | 9/25 - 10/1 | 29 | 27 | 2 | 0 - Learned JWT, Swagger, and Expo Go 2 - Design backend code using express and sqlite database. Using JWT to achieve authentication. Using swagger to produce API documents. 3 - Implemented backend code including database, models, and routes. Debug JWT code. 4 - Implemented small backend test case using jest and supertest 5 - Collaborated with Dexiao to implemented JWT and test in backend code 6 - Used React Native (expo) to create frontend project. Used backend API for small frontend demo. | 2 |  | 3 | 10 | 5 | 2 | 5 |  | ChatGPT has been helpful during this week. It helps to research for the best tools that are going to be used for our project. Since our project does not require large database, sqlite is better than other database. It also suggested that swagger can achieve producing backend API code. For security, GPT suggested that JWT was a good choice. It also confirmed that using Google account would be safer | 1. setup backend and frontend code 2. backend code implemented | need to create one more table in database to store user study history | status: open plan: implement if needed. Still waiting for frontend code to be implemented | start to work with frontend code: adding some screen and connect frontend code with backend APIs | 10
4 | 10/2 - 10/8 | 29 | 27.5 | 1.5 | 0 - Learned how to set up CI on github and the differences between different kinds of tests. Learned how docker works. 3 - Implemented buddy model, buddy routes, and study_buddies table in database 4 - Implemented backend tests including unit tests, integration tests, acceptance tests, and systesms test 5- Bug found during system testing. Communicated with Dexiao to fix energy decay method. 6 - Set up backend CI. Set up docker file. 7 - STD and SDD file | 1 |  |  | 10 | 10 | 0.5 | 3 | 3 |  | 1. backend code (sqlite database including several tables, different models, different routes) 2. backend tests (unit tests for middleware, integration tests for models, acceptance tests for routes, system tests for user stories) 3. backend testing doc part in STD file. Database design part in SDD file. |  |  | Have full workflow tested successfully on backend. Connect backend API endpoint to frontend. | 20
5 | 10/9 - 10/15 | 12 | 11 | 1 | 3 - Implemented Swagger for buddy related class. Implemented comments code. 4 - Bug found on develop branch with docker 5 - Communicated with Shinu about Docker bugs in develop branch 7 - SDD file design and software architecture section. Iteration 1 slides made. |  |  |  | 6 | 0.5 | 0.5 |  | 4 | AI is helpful for giving slides layout. ChatGPT provides me with the agenda of my slides and I can easily put in relative elements in each slide page | 1. SDD files and iteration 1 slides. | I newed a branch and put too much things in the branch. When merging problem occurs, I was having hard time to find the issues. | status: open plan: need to new another more specific branch and put in relative work and merge before put in other works. | Connect backend API endpoint to frontend | 10
6 | 10/16 - 10/22 | 18.5 | 17 | 1.5 | 3 - Implemented frontend login screen to connect to backend API. Integrate Junzhe's UI login page in to this version. Implemented stats routes and models in backend. Implemented AuthContext on frontend to handle authentication and asycStorage. 4 - Manual test whether login page works successfully with backend or not. Implemented API and integration tests for routes and models. Implemented frontend test for home, AuthContext, and LoginForm. Setup frontend test environment. 5 - Communicated with team about the User stories. Communicated with Junzhe about his login code. 6 - Set up frontend .env and let team knows how to run frontend with environment variables. |  |  |  | 8 | 5 | 2 | 2 |  | When using localhost in frontend to connect the backend endpoint API, it always fails. ChatGPT has been really helpful and conducted me to try to use IPv4 which made the connection successful. GPT also helps to suggest that we should keep different .gitignore files in different folders. Link:https://chatgpt.com/share/68f7d559-63dc-8004-96b6-92be145197ff |  | When connecting to endpoint APIs, localhost can not be used. | status: close By changing localhost to IPv4 address, the endpoint API is successfully connected in frontend. |  | 10
7 | 10/23 - 10/29 | 12.5 | 10 | 2.5 | 3 - Implemented frontend statistics screen including stats card and calendar. 5 - Communicated with Dexiao about front end unit tests. Suggested a better way for him to manage Github repo. 7 - Tried to merge develop with frontend_stats branch. Merging failed due to multiple people making changes on the branch. |  |  |  | 4 |  | 2 |  | 4 |  | Login frontend screen. |  |  |  | 10
8 | 10/30 - 11/5 | 9 | 8 | 1 | 7 - Initial route debug. Used different branch to merge frontend calendar into develop. Wrote testing metrics on STD file. Update class diagram on SPPP file. Reviewed hotfix pull requet and other pull requests. | [7 empty] | 8 |  | STD file, SDD file, updated | Team members are not reviewing pull requests. | status: open Communication needed among team members. |  | 20
9 | 11/6 - 11/12 | 4 | 3 | 1 | 3 - Navigation bar implemented |  |  |  | 3 | [9 empty] | 8
10 | 11/13 - 11/19 | 4 | 3 | 1 | 3 - Calendar screen UI improved. Calendar bugs fixed. |  |  |  | 3 | [9 empty] | 8
11 | 11/20 - 11/26 | 5 | 4 | 1 | 3 - Backend deployed on render. Home screen fetch data implemented. When study buddy died, prompt implemented. |  |  |  | 4 |  |  |  |  | ChatGPT has been helpful with the cloud deployment. It suggests the best fit platform render for our project and provided with handson instruction to deploy our server on render. |  | Render free account will sleep the server if it is not pinged every 15 minutes. Since we are using SQLite, the data in the database will be removed everytime the server sleep and awake. | status: open To solve this problem, we can deploy the database seperately on turso to make sure the database is persistent. | Finalize our project code and files. Prepare for the final presentation. | 8
12 | 11/27 - 12/3 | 7.5 | 6 | 1.5 | 4 - Manual testing implemented. 5 - Pull requests review before code freeze. 7 - Final Presentation Slides made. STD file updated. Read through SDD and SPPP file to make sure everything is update. Communicated with other team members to discuss the presentation content. |  |  |  |  | 1 | 1 |  | 4 |  | STD file updated. Final presentation slides made.