## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/11-9/24 | Finished SPPP Created first draft of app Decided on app Analyzed potential risks | 1. Put GitHub repo in the wrong location 2. Took too much time debugging 3. Jira was not visible to all members | 4. Not using Jira 5. Leaving work to last minute when others are reliant on said work 6. Member missed meeting | 1. Resolved 2. Use AI to help with debugging 3. Resolved 4. Create standards and present at meeting 5. Set deadlines for individual pieces that other work relys on 6. All members will be present in-person for meetings | 0 | 0 | 6 | 3 | 3 | 94.5 | 78.5 | 16 | 12.5 | 22.5 | 10 | 14.5 | 3 | 15 | 6
1 | 9/25-10/15 | Created Database and APIs Created backbone for frontend | 1. Tests were not working on all computers 2. Difficulties setting up Docker | 2. Lack of communication - leading to duplicate work | 1. Work as a team to debug problem 2. Resolved 3. Everyone create and use Jira, everyone push to GitHub more frequently, make smaller pull requests | 5 | 13 | 17 | 12 | 7 | 274 | 254 | 20 | 36 | 25 | 35 | 55.5 | 23.5 | 16 | 53
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Melissa Cron
Your Lead Roles: Project Leader, Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 6 | 4 | 2 | 0 - learning 1 - Created 1st draft of Requirement Document 2 - design 3 - implementation 4 - test 5 - Scheduled meeting, used meeting to determine project choice, answered questions about GitHub 6 - setting up GitHub 7 - unclassified |  | 2 |  |  |  | 1 | 1 |  |  | 1. Write first draft requirements document 2. Finished lab 1 | 1. Project subject was changed multiple times 2. Meeting ran long | 1. During our second meeting, the entire group decided on a project subject and it will not be changed now 2. Team leader (me) will create better plan before meetings and try to stick to it | 0 - learn how react interacts with mobile devices 1 - change requirements document to fit ideas from group 2 - design 3 - implementation 4 - test 5 - communication/management 6 - set up personal coding enviroment and jira 7 - unclassified | 5
2 | 9/18 - 9/24 | 4.5 | 4 | 0.5 | 0 - learning 1 - requirement analysis 2 - design 3 - created README.md and formatted team.md 4 - test 5 - meeting notes, helped people join Jira, added to risk management document, did Management Plan in SPPP document 6 - moved github repo to correct location 7 - worked on iteration 0 presentation |  |  |  | 0.5 |  | 2 | 0.5 | 1 |  | 1. wrote meeting notes 2. added to risk management document 3. did management plan in SPPP document 4. worked on iteration 0 presentation | 1. People are not creating nor tracking Jira tickets 2. Individual pieces are not finished soon enough to do the work that requires them | 1. Create standards and present at meeting 2. Set better deadlines | 0 - learning 1 - requirement analysis 2 - design 3 - create first interface 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | 5
3 | 9/25 - 10/1 | 12.5 | 11.5 | 1 | 0 - how to use Jira 1 - turned requirements document into Jira Epics 2 - design 3 - Moved pages from html to React, moved the css, and created the timer for the studying page 4 - test 5 - reviewed other members commits 6 - set up Expo Go 7 - unclassified | 1 | 0.5 |  | 8.5 |  | 0.5 | 1 |  | Consulted ChatGPT about how to use specific React Native functions. |  | 1. code for webpages written in HTML instead of React Native | 1. I rewrote them in React Native | 0 - learning 1 - requirement analysis 2 - design 3 - create interface for goals 4 - review other people's code 5 - communication/management 6 - help member set up GitHub 7 - unclassified | 8
4 | 10/2-10/8 | 6.5 | 5 | 1.5 | 0 - learning 1 - create 2 stories 2 - created 1st draft for Buddies 3 - reviewed pull requests 4 - test 5 - communication/management 6 - failed to get Docker to work 7 - unclassified |  | 1 | 1 | 0.5 |  |  | 2.5 |  |  | 1. Worked on lab 2 | 1. Could not get Docker working 2. Kimi wrote code for a section of the project I already finished the code for | 1. Ask for help from Shinu our Configuration leader 2. He will pull from GitHub and copy over only the code that is not already existing | 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - get docker working 7 - unclassified
5 | 10/9-10/15 | 8.5 | 7.5 | 1 | 0 - consulting software professionals about how to be a better project leader 1 - requirement analysis 2 - design 3 - prepared my branch for pushing by adding comments, fixed accessbility roles 4 - fixed broken API tests 5 - messaging people to make sure the documents get done on time 6 - finally got Docker working 7 - updated SDD, summary for progress report | 2 |  |  | 1.5 | 1 | 0.5 | 0.5 | 2 | I used AI to figure out how to fix a broken test and a broken expo command. It gave me a few different possible solutions, one of which was correct. | 1. updated SPP 2. worked on SDD 3. did summary for progress report | 1. A new page was created without first pulling the existing pages - thus not following the formatting standards 2. A significant amount of work is being done but not ending up on GitHub. I do not know where the code is | 1. The person who did this will pull the existing work and update to match that work 2. Talk to the members involved and impress on them that any work needs to be communicated and updated. Also, encourage smaller pull requests | 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified
0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified

## Dexiao Zhang
Your Lead Roles: Design & Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 11 | 9 | 2 | 0 - Discussed project requirements 1 - studied git ，GitHub ，I/O，HTTP 2 - work on sppp6 | 1 | 7 | 1 | [5 empty] | chatgpt for learning git and so on | set the enviorment about git,write sppp6 |  |  |  | 9 | backend develop
2 | 9/18 - 9/24 | 9 | 8 | 1 | 0 - work on lab1 and write the report 1 - learn how to use stocker and jira 2 - write the lab2 3 - learn the framework we use in project | 1 | 1 | 2 | 4 |  |  |  |  | chatgpt for learning jira and how to set the enviorment about stocker | search the framework,commit profile to github |  |  |  | 9
3 | 9/25-10/1 | 22 | 21 | 1 | 0 - Researched Docker, Express, JWT, and SQLite integration for backend authentication. 1 - Set up backend project structure (server.js, db.js, routes/, models/) and environment configuration using .env and dotenv. 2 - Implemented user registration and login APIs using bcrypt + JWT for secure authentication. 3 - Debugged token verification middleware (auth.js) and ensured protected routes work correctly with JWT. 4 - Collaborated with teammate Bohan on user endpoints and database initialization. 5 - Configured Swagger documentation for backend API endpoints. 6 - Created early unit tests for /api/users/register and /api/users/login routes using Jest and Supertest, verifying 200/400/401 responses. | 4 | 3 | 4 | 3 | 2 | 2 | 3 |  | Used ChatGPT occasionally for syntax debugging and Jest error explanations. Also used it for writing sample curl requests and test setup examples. | Built and tested backend authentication module (JWT). Added working API documentation through Swagger. Contributed to early unit test coverage for /api/users. | JWT token not recognized across requests SQLite path errors in Windows environment Swagger not rendering new endpoints | Fixed by adding consistent Authorization header in middleware Fixed by using path.resolve(process.cwd(), DB_PATH) Fixed by refreshing swaggerSpec registration in server.js | 1.Implemented SQLite models for each module and linked them via foreign keys 2.Added energy decay logic to Buddy model to simulate health/energy drop over time. | 20
4 | 10/2-10/8 | 26 | 25 | 1 | 0 - Extended backend APIs to include Buddy, Profile, Settings, and Study routes. 1 - Implemented SQLite models for each module and linked them via foreign keys. 2 - Wrote and debugged integration and system tests (system.test.js, buddyAPI.test.js, etc.) using Jest and Supertest. 3 - Set up .env.test and __tests__/setupEnv.js to run isolated test databases automatically. 4 - Fixed test-related database issues (foreign key constraint, missing table) and improved test coverage. 5 - Added energy decay logic to Buddy model to simulate health/energy drop over time. 6 - Worked closely with Bohan to merge backend CI branch and ensure all endpoints pass authentication + test validations. 7 - Assisted frontend team with API integration for login and buddy features. | 4 | 2 | 5 | 3 | 2 | 3 | 4 | 2 | Used ChatGPT for explaining SQLite ON CONFLICT behavior and schema design tips. Verified all AI suggestions manually before committing to the repository. | Completed backend models and routes for all core features. Established and debugged automated testing pipeline. Validated energy decay logic and database schema consistency. Contributed to CI readiness for backend testing environment. | Jest tests timing out due to foreign key constraints Test database using incorrect path 500 errors during CI runs Some endpoints returning 401 in tests | Resolved by reordering table deletion and enabling PRAGMA foreign_keys = OFF during cleanup Fixed by resetting DB_PATH to ./db/test.sqlite under test mode Traced to missing start_time/end_time columns; fixed in schema Added consistent token validation middleware |  | 15
5 | 10/9-10/15 | 9 | 8 | 1 | 0 - Prepare the presentation for Iteration 1 1 - Achieved decay value 2 - SDD file design and software architecture section. | 2 | 4 | 2 | [5 empty] | Used ChatGPT selectively for test script review | improve energy decay logic to Buddy model which all pass the test |  |  | achieve personalized study rewards | 15

## Junzhe Chen
Your Lead Roles: Security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 8 | 6 | 2 | 0 - learning 1 - Study Git 2 - design the basic UI 3 - implementation 4 - test 5 - meeting 6 - setting up GitHub | 2 | 2 | 1 | 1 | 1 | 1.5 | 1 | 0 | Chatgpt, Midjourney | Write first draft document Finished lab 1 | project subject change many times | in the second meeting, we decide the subject | do the demo of our project. work on pres | 5
2 | 9/18 - 9/24 | 11.5 | 11 | 0.5 | 0 - learning use AI graph 1 - write on lab 1 2 - SPPP update 3 - project 4 - test | 1 | 1 | 1 | 6 | 2 | 0 | 0 | 0 | chatgpt, gemini | wrote meeting notes added to risk management document did management plan in SPPP document write a demo of our project | use many time to debug | used Ai | do the more detail | 10
3 | 9/25 - 10/1 | 21 | 20 | 1 | 0 - learning Expo Go, Native 1 - Use ant-icon to beautify the UI 2 - Add setting, and study time display 3 - test 5 - find click sound and buddy picture | 4 | 3 | 10 | 2 | 0 | 1 | 0 | 0 | Chatgpt, Midjourney, gemini, nano banana | Frontend study timer page Connect all page in the frontend | need more resourse to build UI | Try to use more professionalism tools | Make the program run | 10
4 | 10/2 - 10/8 | 31.5 | 30 | 1.5 | 0 - learning Pixso, Figma, Flutter 1 - Use Figma to create a demo of home page 2 - Use Pixso to build a calender page 3 - Test two pages | 5 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | Chatgpt, Midjourney, gemini, nano banana, Figma, Pixso | Calender page Home page Buddy information page | Build a beautiful page is too difficult for me | Learned Figma and use Figma to build my page | Try to beautify other pages. | 10
5 | 10/9 - 10/15 | 8 | 7 | 1 | 0 - learning React native, Expo go 1 - connect html.file to React native | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Chatgpt, deepseek | Personal information page. | Many files can run normally individually, but the buttons inside cannot be used to switch pages. | Solve the issue in the next week. | Try writing all the files in html | 10

## Ittoop Shinu Shibu
Your Lead Roles: Configurations Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/11-09/17 | 6 | 3 | 3 | 6 - Set up Jira and configure github 1 - worked on SPPP 1 - Researched on CI/CD, branching and code review strategies 1 - Researched on frameworks 5 - Discussed what our project is going to be about |  | 2 |  |  |  | 3 | 1 |  | ChatGPT - for research into the configuration management portion of the SPPP | 1. Worked on the configuration management portion of the SPPP 2. Conducted research into how to implement CI/CD 3. Set up github repo 4. Set up jira board for the team 5. Looked into the different frameworks we could potentially use for our application 6. Researched branching strategies 7. Researched code review strategies to implement for the team | 1. We were unsure of what application we were going to build for our project 2. The Jira board was not visible to everyone | 1. Resolved, we went through a couple rounds of discussions and decided on what we are building 2. Resolved, made the jira board visible to everyone | 1 - continue to work on SPPP 1 - continue research for the SPPP configuration management portion of the document | 2
2 | 9/18-9/24 | 5 | 3.5 | 1.5 | 6 - Commited changes to new github repo and reviewed PR as the old one was incorrect 1 - Continued to work on SPPP 1 - Continued to research for SPPP on configuration management 1 - Added risks of configuration management into risk document 5 - Went through deliverables and blockers in group meeting in stand up style 7 - worked on powerpoint presentation on group project |  | 2 |  |  |  | 0.5 | 0.5 | 1 | ChatGPT - for research into the configuration management portion of the SPPP | 1. Completed the configuration management portion of the SPPP 2. Conducted research into configuration management 3. Committed any missing changes from old github repo to the new repo 4. Worked on powerpoint presentation on group project 5. Added in configuration management risks into risk document | 1. We realised that the previous repo we created was incorrect and our commits needed to be shifted | 1. Resolved, the old repos contents were shifted to the new repo | 1 - Begin working on iteration 1 2 - set up rulesets on github for branching and clean up branches 3 - begin setting up CI/CD | 6
3 | 9/25-10/1 | 10 | 9 | 1 | 6 - Started to set up CI/CD 6 - Set up git to autodelete branches 6 - Added in code scanning for security 5 - Discussed and agreed on CI/CD approach. Linting and testing to be managed by CI/CD. No pull requests to be merged without the passing of the tests once CI/CD has been setup. Also discussed others progress on their items. 0 - Read up on setting up jest and testing for react native applications 0 - Read up on linting packages using for react native applications | 2 |  |  |  |  | 1 | 7 |  | ChatGPT - for research into CI/CD setup, bug fixing issues with CI/CD setup Github Copilot - for creation of files for CI/CD, bug fixing issues with CI/CD setup | 1. Researched what a CI/CD setup should look like by looking at old repos submitted for this class and researching via ChatGPT. 2. Set up CI/CD for frontend with linting functionality for the time being, as the test setup still had a lot of issues that needed to be fixed. Backend code was not in the branch I was referring to yet so I could only create code for the frontend 3. Set up git to autodelete branches | 1. Faced a lot of issues with setting up CI/CD on the frontend code. We encountered numerous parse issues with Babel, TypeScript, and Flow in the test setup, which took us hours to debug. Most of the time was spent debugging the code to fix this issue. | 1. Not resolved, this will be pushed to next week. | 1. Continue working on getting CI/CD set up | 10
4 | 10/2-10/8 | 15 | 14 | 1 | 6 - Continue setting up CI/CD 6 - Set up docker for our project 0 - read up on how docker works 5 - Discussed issues that I am facing on the CI/CD and what I should provide for docker to the team for lab 2 during team meeting. Also discussed others progress on their items. | 1 |  |  |  |  | 1 | 13 |  | ChatGPT - bug fixing issues with CI/CD setup Gordon (Docker's Agent) - Quick start guide on docker, creation of docker files and bug fixing | 1. Continued trying to get CI/CD set up. I tried to create mocks to circumvent the type script + flow parse errors jest was throwing 2. Set up docker for the project, divided into backend and frontend. provided the docker files to the team and asked the team to review the code | 1. Continued to face issues with this even with creating mocks this week. Most of my time was spent on debugging this issue. Also tried to look at other teams code but no one seems to have used react native. | 1. Not resolved, this will be pushed to next week. | 1. Continue working on getting CI/CD set up | 10
5 | 10/9-10/15 | 18 | 17 | 1 | 6 - Finish setting up CI/CD 7 - Code review 4 - Bug found in develop branch due to docker 5 - Discussed what we need to finish up for the upcoming iteration of the project. 7 - Work on class diagrams for SDD |  |  |  |  | 3 | 1 | 12 | 2 | ChatGPT - bug fixing issues with CI/CD setup Github Copilot - Help to create an initial class diagrams based on our code. | 1. Managed to get the CI/CD setup for both backend (after backend code was pulled into my branch this week) and frontend. Managed to fix the issue of setting up jest switching to jsdom instead of using jest-expo. It was quite hard to fix this, a large amount of time was spent debugging this issue. 2. Completed code review on the completeWebsiteLayout branch. This branch contained all the frontend code for iteration 1. 3. Worked on class diagram for SDD 4. Checked everyone else's additions to the project before we submit 5. Fixed bug where there was a package missing in package.json in the develop branch |  |  | 1. To pick up tickets from the icebox story items on "Recommend study goals based on history and research" and "Global and friends leaderboard for study progress" | 10
6
7
8
9
10
11
12
13
14
15

## Bohan Lin
Your Lead Roles: Design & Implementation Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 11 | 9 | 2 | 0 - Studied Agile, scrum, and Jira 1 - Discussed project requirements 2 - Designing the technology stack for the project | 1 | 3 | 5 | [5 empty] | Use ChatGPT for research technology stack that will be used in the project | 1. Research possible stack that will be used |  |  | finish iteration 0 with required documents filled | 10
2 | 9/18 - 9/24 | 8 | 7.5 | 0.5 | 0 - Review course material and documents 1 - Work on lab1 and lab1 report 5 - Work on SPPP files and SPPP_RiskManagement 6 - Set up Github and Jira | 1 | 1 |  |  |  | 5 | 0.5 |  | Use ChatGPT for research related work of our project | 1. Set up git, push team.md to lab1 branch 2. Write 2 sections of SPPP |  |  | start iteration 1 with demo code | 10
3 | 9/25 - 10/1 | 29 | 27 | 2 | 0 - Learned JWT, Swagger, and Expo Go 2 - Design backend code using express and sqlite database. Using JWT to achieve authentication. Using swagger to produce API documents. 3 - Implemented backend code including database, models, and routes. Debug JWT code. 4 - Implemented small backend test case using jest and supertest 5 - Collaborated with Dexiao to implemented JWT and test in backend code 6 - Used React Native (expo) to create frontend project. Used backend API for small frontend demo. | 2 |  | 3 | 10 | 5 | 2 | 5 |  | ChatGPT has been helpful during this week. It helps to research for the best tools that are going to be used for our project. Since our project does not require large database, sqlite is better than other database. It also suggested that swagger can achieve producing backend API code. For security, GPT suggested that JWT was a good choice. It also confirmed that using Google account would be safer | 1. setup backend and frontend code 2. backend code implemented | need to create one more table in database to store user study history | status: open plan: implement if needed. Still waiting for frontend code to be implemented | start to work with frontend code: adding some screen and connect frontend code with backend APIs | 10
4 | 10/2 - 10/8 | 29 | 27.5 | 1.5 | 0 - Learned how to set up CI on github and the differences between different kinds of tests. Learned how docker works. 3 - Implemented buddy model, buddy routes, and study_buddies table in database 4 - Implemented backend tests including unit tests, integration tests, acceptance tests, and systesms test 5- Bug found during system testing. Communicated with Dexiao to fix energy decay method. 6 - Set up backend CI. Set up docker file. 7 - STD and SDD file | 1 |  |  | 10 | 10 | 0.5 | 3 | 3 |  | 1. backend code (sqlite database including several tables, different models, different routes) 2. backend tests (unit tests for middleware, integration tests for models, acceptance tests for routes, system tests for user stories) 3. backend testing doc part in STD file. Database design part in SDD file. |  |  | Have full workflow tested successfully on backend. Connect backend API endpoint to frontend. | 20
5 | 10/9 - 10/15 | 12 | 11 | 1 | 3 - Implemented Swagger for buddy related class. Implemented comments code. 4 - Bug found on develop branch with docker 5 - Communicated with Shinu about Docker bugs in develop branch 7 - SDD file design and software architecture section. Iteration 1 slides made. |  |  |  | 6 | 0.5 | 0.5 |  | 4 | AI is helpful for giving slides layout. ChatGPT provides me with the agenda of my slides and I can easily put in relative elements in each slide page | 1. SDD files and iteration 1 slides. | I newed a branch and put too much things in the branch. When merging problem occurs, I was having hard time to find the issues. | status: open plan: need to new another more specific branch and put in relative work and merge before put in other works. | Connect backend API endpoint to frontend | 10

## Qiuting Zhao
Your Lead Roles: Design & Implementation Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 7.5 | 6.5 | 1 | 0 - research different stack, install development tools and learn 1 - analyzed target users, confirmed app’s overall style and aesthetic direction 5 - attended project meeting and documented meeting notes. 6 - set up coding environment | 3 | 1.5 |  |  |  | 1 | 1 |  | Use chatgpt to research and compare different stacks | 1. Write meeting notes 2. Set up git 3. Finished Lab1 | The type of project was hesitant for a long time | Solved, made final decision during 2nd meeting | 0 - Learn how React works 2 - Design some mini game prototypes 7 - Finished iteration0 documents | 10
2 | 9/18 - 9/24 | 7 | 7 | 0 | 0 - learn React and Jira, find a lot of mini game prototype online 3 - implement some mini game to try and test 5 - work on Proposed High level Requirements in SPPP file, add to RiskManagement file 6 - join the github repo | 2.5 |  |  | 3 |  | 1 | 0.5 |  |  | 1. Write one section of SPPP 2. Add to RiskManagement file | Missed group meeting | Will go in-person in the future | 5 - Discuss soft friction alternative for iOS device restrictions | 10
3 | 9/25 - 10/1 | 7.5 | 6.5 | 1 | 0 - learn expo, RN, RN web 5 - attended project meeting and documented meeting notes. 6 - set up coding environment | 3 | 1.5 |  |  |  | 1 | 1 |  | Use chatgpt to research and compare different stacks | 1. Write meeting notes 2. Set up git 3. Finished Lab1 | The type of project was hesitant for a long time | Solved, made final decision during 2nd meeting | 0 - Learn how React works 2 - Design some mini game prototypes 7 - Finished iteration0 documents | 10
4 | 10/2 - 10/8 | 8.5 | 7 | 1.5 | 0 - learn React and Jira, find a lot of mini game prototype online 3 - implement some mini game to try and test 5 - work on Proposed High level Requirements in SPPP file, add to RiskManagement file 6 - join the github repo | 2.5 |  |  | 3 |  | 1 | 0.5 |  |  | 1. Write one section of SPPP 2. Add to RiskManagement file | Missed group meeting | Will go in-person in the future | 5 - Discuss soft friction alternative for iOS device restrictions | 10
5 | 10/9 - 10/15 | 8 | 7 | 1 | 0 - learn React and Jira, find a lot of mini game prototype online 3 - implement some mini game to try and test 5 - work on Proposed High level Requirements in SPPP file, add to RiskManagement file 6 - join the github repo | 2.5 |  |  | 3 |  | 1 | 0.5 |  |  | 1. Write one section of SPPP 2. Add to RiskManagement file | Missed group meeting | Will go in-person in the future | 5 - Discuss soft friction alternative for iOS device restrictions | 10