## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/11-9/24 | Finished SPPP Created first draft of app Decided on app Analyzed potential risks | 1. Put GitHub repo in the wrong location 2. Took too much time debugging 3. Jira was not visible to all members | 4. Not using Jira 5. Leaving work to last minute when others are reliant on said work 6. Member missed meeting | 1. Resolved 2. Use AI to help with debugging 3. Resolved 4. Create standards and present at meeting 5. Set deadlines for individual pieces that other work relys on 6. All members will be present in-person for meetings | 0 | 0 | 6 | 3 | 3 | 87.5 | 67.5 | 16.5 | 12.5 | 22.5 | 10 | 14.5 | 3 | 15 | 6
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Melissa Cron
Your Lead Roles: Project Leader, Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 6 | 4 | 2 | 0 - learning 1 - Created 1st draft of Requirement Document 2 - design 3 - implementation 4 - test 5 - Scheduled meeting, used meeting to determine project choice, answered questions about GitHub 6 - setting up GitHub 7 - unclassified |  | 2 |  |  |  | 1 | 1 |  |  | 1. Write first draft requirements document 2. Finished lab 1 | 1. Project subject was changed multiple times 2. Meeting ran long | 1. During our second meeting, the entire group decided on a project subject and it will not be changed now 2. Team leader (me) will create better plan before meetings and try to stick to it | 0 - learn how react interacts with mobile devices 1 - change requirements document to fit ideas from group 2 - design 3 - implementation 4 - test 5 - communication/management 6 - set up personal coding enviroment and jira 7 - unclassified | 5
2 | 9/18 - 9/24 | 4.5 | 4 | 0.5 | 0 - learning 1 - requirement analysis 2 - design 3 - created README.md and formatted team.md 4 - test 5 - meeting notes, helped people join Jira, added to risk management document, did Management Plan in SPPP document 6 - moved github repo to correct location 7 - worked on iteration 0 presentation |  |  |  | 0.5 |  | 2 | 0.5 | 1 |  | 1. wrote meeting notes 2. added to risk management document 3. did management plan in SPPP document 4. worked on iteration 0 presentation | 1. People are not creating nor tracking Jira tickets 2. Individual pieces are not finished soon enough to do the work that requires them | 1. Create standards and present at meeting 2. Set better deadlines | 0 - learning 1 - requirement analysis 2 - design 3 - create first interface 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | 5
3 |  | 0 | 0 |  | 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified

## Dexiao Zhang
Your Lead Roles: Design & Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 9 | 7 | 2 | 0 - Discussed project requirements 1 - studied git ，GitHub ，I/O，HTTP 2 - work on sppp6 | 1 | 7 | 1 | [5 empty] | chatgpt for learning git and so on | set the enviorment about git,write sppp6 |  |  |  | 9 | backend develop
2 | 9/18 - 9/24 | 8 | 7 | 1 | 0 - work on lab1 and write the report 1 - learn how to use stocker and jira 2 - write the lab2 3 - learn the framework we use in project | 1 | 1 | 2 | 4 |  |  |  |  | chatgpt for learning jira and how to set the enviorment about stocker | search the framework,commit profile to github |  |  |  | 9

## Junzhe Chen
Your Lead Roles: Security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 8 | 6 | 2 | 0 - learning 1 - Study Git 2 - design the basic UI 3 - implementation 4 - test 5 - meeting 6 - setting up GitHub | 2 | 2 | 1 | 1 | 1 | 1.5 | 1 | 0 | Chatgpt, Midjourney | Write first draft document Finished lab 1 | project subject change many times | in the second meeting, we decide the subject | do the demo of our project. work on pres | 5
2 | 9/18 - 9/24 | 11 | 7 | 1 | 0 - learning use AI graph 1 - write on lab 1 2 - SPPP update 3 - project 4 - test | 1 | 1 | 1 | 6 | 2 | 0 | 0 | 0 | chatgpt, gemini | wrote meeting notes added to risk management document did management plan in SPPP document write a demo of our project | use many time to debug | used Ai | do the more detail | 6

## Ittoop Shinu Shibu
Your Lead Roles: Configurations Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/11-09/17 | 6 | 3 | 3 | 6 - Set up Jira and configure github 1 - worked on SPPP 1 - Researched on CI/CD, branching and code review strategies 1 - Researched on frameworks 5 - Discussed what our project is going to be about |  | 2 |  |  |  | 3 | 1 |  | ChatGPT - for research into the configuration management portion of the SPPP | 1. Worked on the configuration management portion of the SPPP 2. Conducted research into how to implement CI/CD 3. Set up github repo 4. Set up jira board for the team 5. Looked into the different frameworks we could potentially use for our application 6. Researched branching strategies 7. Researched code review strategies to implement for the team | 1. We were unsure of what application we were going to build for our project 2. The Jira board was not visible to everyone | 1. Resolved, we went through a couple rounds of discussions and decided on what we are building 2. Resolved, made the jira board visible to everyone | 1 - continue to work on SPPP 1 - continue research for the SPPP configuration management portion of the document | 2
2 | 9/18-9/24 | 4 | 2 | 1.5 | 6 - Commited changes to new github repo and reviewed PR as the old one was incorrect 1 - Continued to work on SPPP 1 - Continued to research for SPPP on configuration management 1 - Added risks of configuration management into risk document 5 - Went through deliverables and blockers in group meeting in stand up style 7 - worked on powerpoint presentation on group project |  | 2 |  |  |  | 0.5 | 0.5 | 1 | ChatGPT - for research into the configuration management portion of the SPPP | 1. Completed the configuration management portion of the SPPP 2. Conducted research into configuration management 3. Committed any missing changes from old github repo to the new repo 4. Worked on powerpoint presentation on group project 5. Added in configuration management risks into risk document | 1. We realised that the previous repo we created was incorrect and our commits needed to be shifted | 1. Resolved, the old repos contents were shifted to the new repo | 1 - Begin working on iteration 1 2 - set up rulesets on github for branching and clean up branches 3 - begin setting up CI/CD | 6

## Bohan Lin
Your Lead Roles: Design & Implementation Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 9 | 7 | 2 | 0 - Studied Agile, scrum, and Jira 1 - Discussed project requirements 2 - Designing the technology stack for the project | 1 | 3 | 5 | [5 empty] | Use ChatGPT for research technology stack that will be used in the project | 1. Research possible stack that will be used |  |  | finish iteration 0 with required documents filled | 10
2 | 9/18 - 9/24 | 7.5 | 7 | 0.5 | 0 - Review course material and documents 1 - Work on lab1 and lab1 report 5 - Work on SPPP files and SPPP_RiskManagement 6 - Set up Github and Jira | 1 | 1 |  |  |  | 5 | 0.5 |  | Use ChatGPT for research related work of our project | 1. Set up git, push team.md to lab1 branch 2. Write 2 sections of SPPP |  |  | start iteration 1 with demo code | 10

## Qiuting Zhao
Your Lead Roles: Design & Implementation Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 7.5 | 6.5 | 1 | 0 - research different stack, install development tools and learn 1 - analyzed target users, confirmed app’s overall style and aesthetic direction 5 - attended project meeting and documented meeting notes. 6 - set up coding environment | 3 | 1.5 |  |  |  | 1 | 1 |  | Use chatgpt to research and compare different stacks | 1. Write meeting notes 2. Set up git 3. Finished Lab1 | The type of project was hesitant for a long time | Solved, made final decision during 2nd meeting | 0 - Learn how React works 2 - Design some mini game prototypes 7 - Finished iteration0 documents | 10
2 | 9/18 - 9/24 | 7 | 7 | 0 | 0 - learn React and Jira, find a lot of mini game prototype online 3 - implement some mini game to try and test 5 - work on Proposed High level Requirements in SPPP file, add to RiskManagement file 6 - join the github repo | 2.5 |  |  | 3 |  | 1 | 0.5 |  |  | 1. Write one section of SPPP 2. Add to RiskManagement file | Missed group meeting | Will go in-person in the future | 5 - Discuss soft friction alternative for iOS device restrictions | 10